## Slide 1
LGB
OPERATIONS TECHNOLOGY
October 2026
Plant Digitalization Projects
K.Palayam, P.Palayam, Pongalur, Annur
LGB | Operations Technology

## Slide 2
PROJECT OVERALL LIST
LGB l Operations Technology
S.No | Plant | Line | Task | Description | Start Date | End Date
1 | K.Palayam | RAD | BMW Digitalization | PRISM & Operator Buddy Implementation, Machine Interlock | 01.10.2026 | 30.10.2026
2 | K.Palayam | RAD | BMW Digitalization | Data Collection form Machine | 12.10.2026 | 15.10.2026
3 | K.Palayam | BOSCH | Bosch Digitalization | Data Collection form Machine | 09.10.2026 | 10.10.2026
4 | K.Palayam | BMW | BMW Digitalization | Grinding Machine Datalogging | 09.10.2026 | 09.10.2026
5 | K.Palayam | BOSCH | Bosch Digitalization | Data Collection form Machine | 10.10.2026 | 10.10.2026
6 | Annur | CMBF | Furnace Dashboard | Data logging from furnace | 14.10.2026 | 15.10.2026
7 | Annur | Rotary Furnace | Furnace Dashboard | Data logging from furnace | 19.10.2026 | 30.10.2026
8 | PGR | SQF | Furnace Dashboard | Energy Meter Data Collection from Furnace | 05.10.2026 | 27.10.2026
9 | PGR | SQF | Furnace Dashboard | Furnace Charge in and Charge OUT Data Collection | 05.11.2026 | 12.11.2026
10 | PGR | CNC | CNC Digitalization | Data Collection form Machine | 06.10.2026 | 07.10.2026
11 | P.Palayam | SQF | Furnace Dashboard | Data Collection from Furnace | 07.10.2026 | 07.10.2026
12 | P.Palayam | Chain | Press Dashboard | Data Collection from Stamping Press | 01.11.2026 | 01.11.206
13 | P.Palayam | Daimler | Daimler Line Digitalization | Data Collection from Machines and Showing it in PRISM | 05.10.2026 | 05.11.2026
14 | P.Palayam | Daimler | Daimler Line Automation | Data Collection from COBOT PLC using its tags and display it in Prism | 05.10.2026 | 05.11.2026
15 | P.Palayam | Stellantis | Stellantis Line Digitalization | Data need to pushed from SQLite to MongoDB | 12.10.2026 | 13.10.2026
16 | Vaiyampalayam | SQF | Furnace Dashboard | Data Collection from Furnace | 27.10.2026 | 30.10.2026
17 | Nagpur | Sprocket | CNC Digitalization | Data Collection from CNC Machines | 01.10.2026 | 01.12.2026
18 | Nagpur | Sprocket | Press Dashboard | Data Collection from Stamping Press | 01.10.2026 | 01.12.2026

## Slide 3
01
BMW Digitalization
K.Palayam Plant

## Slide 4
LGB l Operations Technology
BMW Line ( OCT PLAN vs ACTUAL )
BMW RAD Line |  |  |  |  |  |  |  |  | 
S.No | Task Description | Responsibility | Planned |  | Actual |  | Status | % Complete | Remarks
 |  |  | Start Date | End Date | Start Date | End Date |  |  | 
1 | New Machines DataLogging | Plant IT | 05-Sep-26 | 25-Sep-26 | 09-Oct-26 | 15-Oct-26 | InProgress | 75% | 4 machines pending for Ethernet
2 | Machine Interlock | Gowtham | 10--Sep-26 | 01-Oct-26 | 01-Oct-26 | 09-Oct-26 | Completed | 100% | -
3 | Operator Buddy Implentation | Gowtham | 01-Aug-26 | 30-Sep-26 | 15-Sep-26 | 17-Oct-26 | InProgress | 80% | Quality Feeder Error Testing is Pending
4 | Grinding Machine Data Collection | MBD | 19-Aug-26 | 22-Sep-26 | 23-Sep-26 | 14-Oct-26 | InProgress | 10% | -
5 | Machine Interlock in B Block | Gowtham | 31-Oct-26 | 31-Nov-26 | - | - | Not Started | - | -
6 | Machine Data Collection in KM-TU-13 using Melss | Gowtham | 01-Oct-26 | 09-Oct-26 | 01-Oct-26 | 09-Oct-26 | Completed | 100% | -

## Slide 5
LGB l Operations Technology
Completed Tasks
KM-TU-13 Data Collection :

## Slide 6
02
Bosch Digitalization
K.Palayam Plant

## Slide 7
LGB l Operations Technology
Bosch Line ( OCT PLAN vs ACTUAL )
Bosch Line |  |  |  |  |  |  |  |  | 
S.No | Task Description | Responsibility | Planned |  | Actual |  | Status | % Complete | Remarks
 |  |  | Start Date | End Date | Start Date | End Date |  |  | 
1 | Old Machines Datalogging | Gowtham | 05-Aug-26 | 25-Aug-26 | 09-Sep-26 | 01-Oct-26 | Completed | 100% | -
2 | New Machines Datalogging | Plant IT | 10-Sep-26 | 01-Oct-26 | 01-Oct-26 | 09-Oct-26 | InProgress | 40% | 6 Macines Pending for IP Assignment
3 | Operator Buddy Implentation | Gowtham | 01-Aug-26 | 30-Sep-26 | 15-Sep-26 | 17-Oct-26 | InProgress | 5% | Edge Device need to Purchase
4 | Deburring Machine DataCollection | Plant Production Team | 19-Aug-26 | 22-Sep-26 | 23-Sep-26 | 14-Oct-26 | InProgress | 10% | Vendor Assistance is pending

## Slide 8
LGB l Operations Technology
Completed Tasks
Bosch Machines Data Collection :

## Slide 9
03
Annur Plant

## Slide 10
LGB l Operations Technology
Annur ( OCT PLAN vs ACTUAL )
Annur |  |  |  |  |  |  |  |  | 
S.No | Task Description | Responsibility | Planned |  | Actual |  | Status | % Complete | Remarks
 |  |  | Start Date | End Date | Start Date | End Date |  |  | 
1 | Elco Device Datalogging | Gowtham | 05-Sep-26 | 15-Sep-26 | 30-Sep-26 | 05-Oct-26 | Completed | 100% | -
2 | CMB Furnace Data Collection | Gowtham | 10-Sep-26 | 01-Oct-26 | 15-Sep-26 | 15-Oct-26 | InProgress | 50% | Out of 2 Furnaces, 1 furnace is Pending
3 | Rotary Furnace Data Collection | MBD | 01-Aug-26 | 30-Sep-26 | 15-Sep-26 | 31-Oct-26 | InProgress | 5% | MBD Visit is Pending

## Slide 11
LGB l Operations Technology
Completed Tasks
Elco Device Data Collection :

## Slide 12
04
Pongalur Plant

## Slide 13
LGB l Operations Technology
Pongalur ( OCT PLAN vs ACTUAL )
Pongalur |  |  |  |  |  |  |  |  | 
S.No | Task Description | Responsibility | Planned |  | Actual |  | Status | % Complete | Remarks
 |  |  | Start Date | End Date | Start Date | End Date |  |  | 
1 | CNC & VMC Data Collection | Plant Electrical | 15-Sep-26 | 15-Oct-26 | 01-Oct-26 | 30-Oct-26 | InProgress | 10% | Relay Wiring is Pending
2 | Operator Buddy Implementation | Plant IT | 20-Sep-26 | 01-Oct-26 | 18-Oct-26 | 07-Nov-26 | InProgress | 10% | Data Collection & Device Purchase is Pending
3 | SQF Data Collection (Charge In and Charge Out) | Plant Electrical | 01-Aug-26 | 30-Sep-26 | 15-Sep-26 | 31-Oct-26 | InProgress | 20% | Wiring is Pending
4 | Energy Meter Data Collection | Plant Electrical | 01-Aug-26 | 15-Sep-26 | 01-Oct-26 | 31-Oct-26 | InProgress | 10% | Approval is given, Device Purchase is Pending

## Slide 14
05
P.Palayam Plant

## Slide 15
LGB l Operations Technology
P.Palayam ( OCT PLAN vs ACTUAL )
P.Palayam |  |  |  |  |  |  |  |  |  | 
S.No | Line | Task Description | Responsibility | Planned |  | Actual |  | Status | % Complete | Remarks
 |  |  |  | Start Date | End Date | Start Date | End Date |  |  | 
1 | SQF | Furnace Data Collection | Plant IT | 15-Sep-26 | 15-Oct-26 | 01-Oct-26 | 30-Oct-26 | InProgress | 50% | Port Access is Pending
2 | Chain | Press Data Collection | Plant Electrical | 20-Sep-26 | 01-Oct-26 | 01-Oct-26 | 07-Nov-26 | InProgress | 10% | Wiring from Machine is Pending
3 | Daimler | Machine Data Collection | Plant IT | 22-Sep-26 | 22-Oct-26 | 30-Sep-26 | 31-Oct-26 | InProgress | 5% | Ethernet is Pending
4 | Daimler | Data Collection from Cobot PLC | Plant IT | 27-Sep-26 | 27-Oct-26 | 01-Oct-26 | 31-Oct-26 | InProgress | 40% | Ethernet and Switch Installation is Pending
5 | Stellantis | OP20 Machine Data Collection | Plant Production | 30-Sep-26 | 30-Oct-26 | 01-Oct-26 | 30-Oct-26 | InProgress | 10% | Device Purchase is Pending

## Slide 16
05
Vaiyampalayam Plant

## Slide 17
LGB l Operations Technology
Vaiyampalayam ( OCT PLAN vs ACTUAL )
Vaiyampalayam |  |  |  |  |  |  |  |  |  | 
S.No | Line | Task Description | Responsibility | Planned |  | Actual |  | Status | % Complete | Remarks
 |  |  |  | Start Date | End Date | Start Date | End Date |  |  | 
1 | SQF | Furnace Data Collection | Gowtham | 15-Aug-26 | 15-Sep-26 | 28-Oct-26 | 30-Oct-26 | InProgress | 50% | -

## Slide 18
06
Nagpur Plant

## Slide 19
LGB l Operations Technology
Nagpur ( OCT PLAN vs ACTUAL )
Nagpur |  |  |  |  |  |  |  |  | 
S.No | Task Description | Responsibility | Planned |  | Actual |  | Status | % Complete | Remarks
 |  |  | Start Date | End Date | Start Date | End Date |  |  | 
1 | CNC Data Collection | Plant IT | 01-Oct-26 | 15-Sep-26 | 13-Nov-26 | 30-Dec-26 | Not Started | 10% | Server PC Purchase is Pending

## Slide 20
Thank You
October 2026
Project progress review
LGB | Operations Technology