## 2-Axis Robot Timeline
2-Axis Industrial Robot Prototype – Complete Development Timeline
Beginner team plan: 12-month development roadmap with dedicated learning, design iterations, procurement delays, commissioning, testing and rework.
Project Assumptions
Project Start | 2027-01-04
Working Days / Week | 5
Estimated Duration | ~52 weeks / 1 year
Current Hardware | Workbench + 1 AC servo + 1 servo drive available; remaining hardware procured in stages.
Main Target | Functional 2-axis industrial robot prototype with safe servo motion, homing, limits, kinematics, coordinated motion, payload testing and documentation.
ID | Phase / Task | Key Deliverable | Department | Duration (working days) | Dependency | Start | Finish | Status | Notes | Manpower Role | Responsibilities | Manpower Qty | Man-Days
1 | Project orientation & robotics fundamentals | Understand robot types, 2-axis architecture, coordinate systems, safety basics | All | 10 |  | 2027-01-04 | 2027-01-15 | Planned | Beginner-paced plan; includes learning, rework and testing. | All | Cross-functional review, integration, documentation and project acceptance. | 1
2 | Requirements definition | Payload, reach, speed, repeatability, workspace, cycle time and safety requirements | Mechanical | 10 | 1 | 2027-01-04 | 2027-01-22 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Design Engineer | CAD, robot architecture, dimensions, drawings, tolerances and design revisions. | 1
3 | Mechanical design fundamentals | Learn CAD, joints, links, bearings, shafts, couplings and tolerances | Mechanical | 15 | 1 | 2027-01-04 | 2027-01-29 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Design Engineer | CAD, robot architecture, dimensions, drawings, tolerances and design revisions. | 1
4 | Servo motor & drive fundamentals | Learn servo construction, encoder, drive modes, alarms and parameter basics | Electrical | 15 | 1 | 2027-01-11 | 2027-01-29 | Planned | Beginner-paced plan; includes learning, rework and testing. | Servo/Drive Engineer | Servo/drive selection, parameters, wiring, commissioning, tuning and fault diagnosis. | 1
5 | Electrical fundamentals & safety | 24V control, 1/3-phase power, grounding, breakers, contactors, E-stop and safety concepts | Electrical | 15 | 1 | 2027-01-11 | 2027-02-05 | Planned | Beginner-paced plan; includes learning, rework and testing. | Electrical Design Engineer | Power/control architecture, schematic, protection, grounding, safety and panel design. | 1
6 | Firmware/controller fundamentals | MCU/PLC basics, GPIO, timers, interrupts, communication and debugging | Firmware | 15 | 1 | 2027-01-18 | 2027-02-05 | Planned | Beginner-paced plan; includes learning, rework and testing. | Firmware Engineer | Controller firmware, I/O, communication, diagnostics, state machine and fault handling. | 1
7 | Hands-on Axis-1 servo bench | Wire existing servo, enable, jog, direction, alarm reset and safe stop | Electrical | 15 | 4,5 | 2027-01-25 | 2027-02-12 | Planned | Beginner-paced plan; includes learning, rework and testing. | Servo/Drive Engineer | Servo/drive selection, parameters, wiring, commissioning, tuning and fault diagnosis. | 1
8 | Encoder & feedback study | Understand encoder signals, resolution, feedback loop and homing principles | Firmware/Controls | 10 | 4,6 | 2027-02-01 | 2027-02-12 | Planned | Beginner-paced plan; includes learning, rework and testing. | Motion Control Engineer | Position/speed control, homing, limits, trajectory, synchronization, calibration and tuning. | 1
9 | Communication study | Pulse/Direction, Modbus/fieldbus or selected drive protocol; document command mapping | Firmware | 15 | 4,6 | 2027-02-01 | 2027-02-19 | Planned | Beginner-paced plan; includes learning, rework and testing. | Firmware Engineer | Controller firmware, I/O, communication, diagnostics, state machine and fault handling. | 1
10 | Mechanical concept v1 | CAD concept, link dimensions, joint arrangement and preliminary assembly | Mechanical | 20 | 2,3 | 2027-02-08 | 2027-03-05 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Design Engineer | CAD, robot architecture, dimensions, drawings, tolerances and design revisions. | 1
11 | Torque/inertia/load calculations | Calculate joint torque, reflected inertia, speed, acceleration and gearbox ratio | Mechanical | 15 | 2,10 | 2027-02-22 | 2027-03-12 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Engineer | Load calculations, gearbox/bearing/shaft/coupling selection, alignment, testing and mechanical validation. | 1
12 | Gearbox and bearing research | Compare planetary/harmonic/cycloidal options, bearings, shafts and couplings | Mechanical | 15 | 11 | 2027-03-01 | 2027-03-19 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Engineer | Load calculations, gearbox/bearing/shaft/coupling selection, alignment, testing and mechanical validation. | 1
13 | Servo/drive sizing & selection | Finalize motor, drive, gearbox and feedback requirements for both axes | Electrical | 15 | 11,12 | 2027-03-08 | 2027-03-26 | Planned | Beginner-paced plan; includes learning, rework and testing. | Servo/Drive Engineer | Servo/drive selection, parameters, wiring, commissioning, tuning and fault diagnosis. | 1
14 | Procurement cycle 1 | RFQs, vendor comparison, purchase and delivery of mechanical/electrical parts | Electrical | 25 | 12,13 | 2027-03-22 | 2027-04-16 | Planned | Beginner-paced plan; includes learning, rework and testing. | Electrical Design Engineer | Power/control architecture, schematic, protection, grounding, safety and panel design. | 1
15 | Mechanical design v2 | Update CAD with actual component dimensions and manufacturability | Mechanical | 20 | 12,13 | 2027-04-05 | 2027-04-30 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Design Engineer | CAD, robot architecture, dimensions, drawings, tolerances and design revisions. | 1
16 | Electrical architecture | Create block diagram, power tree, I/O list, protection and grounding plan | Electrical | 15 | 5,9 | 2027-04-12 | 2027-05-07 | Planned | Beginner-paced plan; includes learning, rework and testing. | Electrical Design Engineer | Power/control architecture, schematic, protection, grounding, safety and panel design. | 1
17 | Controller selection | Compare PLC, industrial PC and MCU options; select controller and I/O | Controls | 10 | 9,16 | 2027-04-26 | 2027-05-14 | Planned | Beginner-paced plan; includes learning, rework and testing. | PLC Engineer | PLC logic, I/O mapping, HMI, sequences, drive communication and interlocks. | 1
18 | Panel schematic & safety architecture | E-stop chain, servo enable, limits, safety relay, fusing and terminals | Electrical | 20 | 16,17 | 2027-05-03 | 2027-05-28 | Planned | Beginner-paced plan; includes learning, rework and testing. | Electrical Design Engineer | Power/control architecture, schematic, protection, grounding, safety and panel design. | 1
19 | Firmware prototype v1 | Basic controller program, digital I/O, communication and diagnostic logging | Firmware | 20 | 6,9,17 | 2027-05-03 | 2027-06-04 | Planned | Beginner-paced plan; includes learning, rework and testing. | Firmware Engineer | Controller firmware, I/O, communication, diagnostics, state machine and fault handling. | 1
20 | Single-axis position control | Command position/speed, read feedback, stop and recover from alarms | Firmware/Controls | 20 | 7,8,19 | 2027-05-24 | 2027-06-18 | Planned | Beginner-paced plan; includes learning, rework and testing. | Motion Control Engineer | Position/speed control, homing, limits, trajectory, synchronization, calibration and tuning. | 1
21 | Single-axis tuning practice | Gain concepts, acceleration/deceleration, overshoot, settling and repeatability | Electrical | 15 | 20 | 2027-06-07 | 2027-07-02 | Planned | Beginner-paced plan; includes learning, rework and testing. | Servo/Drive Engineer | Servo/drive selection, parameters, wiring, commissioning, tuning and fault diagnosis. | 1
22 | Mechanical fabrication preparation | Drawings, tolerances, BOM, machining/fabrication plan and inspection points | Mechanical | 15 | 15 | 2027-05-31 | 2027-07-02 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Design Engineer | CAD, robot architecture, dimensions, drawings, tolerances and design revisions. | 1
23 | Fabrication & machining | Base, links, joint housings, motor mounts and brackets | Mechanical | 30 | 22 | 2027-06-21 | 2027-07-23 | Planned | Beginner-paced plan; includes learning, rework and testing. | Fabrication/Assembly Technician | Fabrication, machining coordination, assembly, fastening and inspection. | 1
24 | Panel procurement & build | Components, enclosure, DIN rail, terminals, protection and wiring | Electrical | 25 | 18 | 2027-06-28 | 2027-07-30 | Planned | Beginner-paced plan; includes learning, rework and testing. | Electrical Technician | Panel assembly, power/control wiring, terminals, connectors and electrical testing. | 1
25 | Axis-1 mechanical assembly | Install gearbox, shaft, bearing, motor, coupling and alignment | Mechanical | 15 | 23 | 2027-07-26 | 2027-08-13 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Engineer | Load calculations, gearbox/bearing/shaft/coupling selection, alignment, testing and mechanical validation. | 1
26 | Axis-1 integrated commissioning | Electrical + servo + mechanical commissioning at low speed | Electrical | 15 | 24,25 | 2027-08-02 | 2027-08-27 | Planned | Beginner-paced plan; includes learning, rework and testing. | Servo/Drive Engineer | Servo/drive selection, parameters, wiring, commissioning, tuning and fault diagnosis. | 1
27 | Axis-1 homing & limits | Home switch, positive/negative limits and software limits | Firmware/Controls | 15 | 26 | 2027-08-16 | 2027-09-10 | Planned | Beginner-paced plan; includes learning, rework and testing. | Motion Control Engineer | Position/speed control, homing, limits, trajectory, synchronization, calibration and tuning. | 1
28 | Axis-1 reliability testing | Repeated cycles, thermal observation, backlash and fault recovery | Mechanical | 15 | 27 | 2027-08-30 | 2027-09-17 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Engineer | Load calculations, gearbox/bearing/shaft/coupling selection, alignment, testing and mechanical validation. | 1
29 | Mechanical design v3 / lessons learned | Correct design issues found during Axis-1 testing | Mechanical | 15 | 28 | 2027-09-13 | 2027-10-01 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Design Engineer | CAD, robot architecture, dimensions, drawings, tolerances and design revisions. | 1
30 | Procurement cycle 2 / missing parts | Order replacements, improved components and Axis-2 parts | Electrical | 20 | 29 | 2027-09-20 | 2027-10-15 | Planned | Beginner-paced plan; includes learning, rework and testing. | Electrical Design Engineer | Power/control architecture, schematic, protection, grounding, safety and panel design. | 1
31 | Axis-2 fabrication & assembly | Build second joint and integrate gearbox, motor, bearing and coupling | Mechanical | 25 | 30 | 2027-10-04 | 2027-10-29 | Planned | Beginner-paced plan; includes learning, rework and testing. | Fabrication/Assembly Technician | Fabrication, machining coordination, assembly, fastening and inspection. | 1
32 | Axis-2 electrical integration | Wire second drive, feedback, limits and controller I/O | Electrical | 15 | 31 | 2027-10-18 | 2027-11-05 | Planned | Beginner-paced plan; includes learning, rework and testing. | Electrical Technician | Panel assembly, power/control wiring, terminals, connectors and electrical testing. | 1
33 | Axis-2 commissioning | Servo setup, direction, jog, alarms and low-speed operation | Electrical | 15 | 32 | 2027-11-01 | 2027-11-19 | Planned | Beginner-paced plan; includes learning, rework and testing. | Servo/Drive Engineer | Servo/drive selection, parameters, wiring, commissioning, tuning and fault diagnosis. | 1
34 | 2-axis homing sequence | Independent and sequential homing for both axes | Firmware/Controls | 15 | 33 | 2027-11-15 | 2027-12-03 | Planned | Beginner-paced plan; includes learning, rework and testing. | Motion Control Engineer | Position/speed control, homing, limits, trajectory, synchronization, calibration and tuning. | 1
35 | 2-axis firmware architecture | Axis abstraction, state machine, fault handling and command interface | Firmware | 20 | 34 | 2027-11-08 | 2027-12-03 | Planned | Beginner-paced plan; includes learning, rework and testing. | Firmware Engineer | Controller firmware, I/O, communication, diagnostics, state machine and fault handling. | 1
36 | Forward kinematics | Implement and validate joint-to-end-effector position calculations | Firmware/Robotics | 20 | 29,35 | 2027-11-22 | 2027-12-17 | Planned | Beginner-paced plan; includes learning, rework and testing. | Robotics Software Engineer | Kinematics, trajectory/application software and robot command handling. | 1
37 | Inverse kinematics | Implement target-position to joint-angle calculations | Firmware/Robotics | 25 | 36 | 2027-11-29 | 2027-12-24 | Planned | Beginner-paced plan; includes learning, rework and testing. | Robotics Software Engineer | Kinematics, trajectory/application software and robot command handling. | 1
38 | Trajectory generation | Acceleration profiles, interpolation and safe coordinated movement | Firmware/Controls | 25 | 37 | 2027-12-06 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Motion Control Engineer | Position/speed control, homing, limits, trajectory, synchronization, calibration and tuning. | 1
39 | 2-axis coordinated motion | Move both axes together to defined positions | Firmware/Controls | 20 | 38 | 2027-12-13 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Motion Control Engineer | Position/speed control, homing, limits, trajectory, synchronization, calibration and tuning. | 1
40 | Jog/manual/auto modes | Implement operator modes, start/stop/reset and safe transitions | Controls | 15 | 35,39 | 2027-12-13 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | PLC Engineer | PLC logic, I/O mapping, HMI, sequences, drive communication and interlocks. | 1
41 | HMI/operator interface | Basic status, position, alarms, mode selection and controls | Controls | 20 | 40 | 2027-12-13 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | PLC Engineer | PLC logic, I/O mapping, HMI, sequences, drive communication and interlocks. | 1
42 | Safety validation | E-stop, limits, servo-off, restart behavior, fault cases and safe state | Electrical | 15 | 40,41 | 2027-12-20 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Electrical Design Engineer | Power/control architecture, schematic, protection, grounding, safety and panel design. | 1
43 | Calibration & zeroing | Joint zero offsets, homing repeatability and coordinate calibration | Firmware/Controls | 20 | 42 | 2027-12-20 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Motion Control Engineer | Position/speed control, homing, limits, trajectory, synchronization, calibration and tuning. | 1
44 | Accuracy/repeatability testing | Measure commanded vs actual positions and repeatability over multiple cycles | Mechanical | 20 | 43 | 2027-12-20 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Engineer | Load calculations, gearbox/bearing/shaft/coupling selection, alignment, testing and mechanical validation. | 1
45 | Payload testing – low load | Test increasing payload while monitoring torque, temperature and vibration | Mechanical | 15 | 44 | 2027-12-27 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Engineer | Load calculations, gearbox/bearing/shaft/coupling selection, alignment, testing and mechanical validation. | 1
46 | Payload testing – target load | Validate target payload and cycle time | Mechanical | 20 | 45 | 2027-12-27 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Engineer | Load calculations, gearbox/bearing/shaft/coupling selection, alignment, testing and mechanical validation. | 1
47 | Endurance/cycle testing | Long-duration repeated operation and thermal monitoring | Firmware | 25 | 46 | 2027-12-27 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Firmware Engineer | Controller firmware, I/O, communication, diagnostics, state machine and fault handling. | 1
48 | Fault injection testing | Power loss, drive alarm, encoder fault, limit activation, communication loss | Firmware | 20 | 47 | 2027-12-27 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Firmware Engineer | Controller firmware, I/O, communication, diagnostics, state machine and fault handling. | 1
49 | Design improvements / final iteration | Mechanical, electrical and firmware corrections from test results | Mechanical | 25 | 48 | 2027-12-27 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Mechanical Design Engineer | CAD, robot architecture, dimensions, drawings, tolerances and design revisions. | 1
50 | Final integrated testing | Full robot test: homing, motion, payload, safety and recovery | Firmware/Controls | 20 | 49 | 2027-12-27 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | Motion Control Engineer | Position/speed control, homing, limits, trajectory, synchronization, calibration and tuning. | 1
51 | Documentation & BOM freeze | CAD, drawings, wiring, source code, parameters, BOM, test reports and SOP | All | 20 | 50 | 2027-12-27 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | All | Cross-functional review, integration, documentation and project acceptance. | 1
52 | Final demo & project review | Demonstration, acceptance checklist, lessons learned and next-generation plan | All | 10 | 51 | 2027-12-27 | 2027-12-31 | Planned | Beginner-paced plan; includes learning, rework and testing. | All | Cross-functional review, integration, documentation and project acceptance. | 1

## 1-Year Manpower Timeline
Month | Phase | Primary Manpower | Main Work
Month 1 | Foundation & requirements | All | Robotics basics, requirements, CAD/electrical/servo/firmware fundamentals
Month 2 | Servo & control learning | Electrical + Firmware | Existing servo bench, encoder, drive communication, basic control
Month 3 | Mechanical concept & sizing | Mechanical + Electrical | CAD concept, torque/inertia, gearbox and servo selection
Month 4 | Detailed design & procurement | Mechanical + Electrical | Mechanical v2, electrical architecture, controller and procurement
Month 5 | Fabrication & panel build | Mechanical + Electrical | Fabrication, panel assembly, wiring and inspection
Month 6 | Axis-1 integration | Mechanical + Electrical + Firmware | Axis-1 assembly, commissioning, homing and limits
Month 7 | Axis-1 testing & Axis-2 build | Mechanical + Controls | Reliability testing, redesign and Axis-2 fabrication
Month 8 | Axis-2 commissioning | Electrical + Firmware | Axis-2 drive/feedback integration, homing and firmware architecture
Month 9 | Kinematics | Firmware/Robotics | Forward/inverse kinematics and basic trajectory
Month 10 | 2-axis coordinated motion | Firmware + Controls | Coordinated motion, jog/auto modes, HMI and safety
Month 11 | Calibration & validation | All | Accuracy, repeatability, payload, endurance and fault testing
Month 12 | Final iteration & release | All | Design improvements, final tests, documentation, BOM freeze and demo

## Gantt
2-Axis Robot – 1-Year Beginner Gantt Chart
[5 empty] | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC
ID | Task | Manpower Role | Start | Finish | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
1 | Project orientation & robotics fundamentals | All | 2027-01-04 | 2027-01-15
2 | Requirements definition | Mechanical Design Engineer | 2027-01-04 | 2027-01-22
3 | Mechanical design fundamentals | Mechanical Design Engineer | 2027-01-04 | 2027-01-29
4 | Servo motor & drive fundamentals | Servo/Drive Engineer | 2027-01-11 | 2027-01-29
5 | Electrical fundamentals & safety | Electrical Design Engineer | 2027-01-11 | 2027-02-05
6 | Firmware/controller fundamentals | Firmware Engineer | 2027-01-18 | 2027-02-05
7 | Hands-on Axis-1 servo bench | Servo/Drive Engineer | 2027-01-25 | 2027-02-12
8 | Encoder & feedback study | Motion Control Engineer | 2027-02-01 | 2027-02-12
9 | Communication study | Firmware Engineer | 2027-02-01 | 2027-02-19
10 | Mechanical concept v1 | Mechanical Design Engineer | 2027-02-08 | 2027-03-05
11 | Torque/inertia/load calculations | Mechanical Engineer | 2027-02-22 | 2027-03-12
12 | Gearbox and bearing research | Mechanical Engineer | 2027-03-01 | 2027-03-19
13 | Servo/drive sizing & selection | Servo/Drive Engineer | 2027-03-08 | 2027-03-26
14 | Procurement cycle 1 | Electrical Design Engineer | 2027-03-22 | 2027-04-16
15 | Mechanical design v2 | Mechanical Design Engineer | 2027-04-05 | 2027-04-30
16 | Electrical architecture | Electrical Design Engineer | 2027-04-12 | 2027-05-07
17 | Controller selection | PLC Engineer | 2027-04-26 | 2027-05-14
18 | Panel schematic & safety architecture | Electrical Design Engineer | 2027-05-03 | 2027-05-28
19 | Firmware prototype v1 | Firmware Engineer | 2027-05-03 | 2027-06-04
20 | Single-axis position control | Motion Control Engineer | 2027-05-24 | 2027-06-18
21 | Single-axis tuning practice | Servo/Drive Engineer | 2027-06-07 | 2027-07-02
22 | Mechanical fabrication preparation | Mechanical Design Engineer | 2027-05-31 | 2027-07-02
23 | Fabrication & machining | Fabrication/Assembly Technician | 2027-06-21 | 2027-07-23
24 | Panel procurement & build | Electrical Technician | 2027-06-28 | 2027-07-30
25 | Axis-1 mechanical assembly | Mechanical Engineer | 2027-07-26 | 2027-08-13
26 | Axis-1 integrated commissioning | Servo/Drive Engineer | 2027-08-02 | 2027-08-27
27 | Axis-1 homing & limits | Motion Control Engineer | 2027-08-16 | 2027-09-10
28 | Axis-1 reliability testing | Mechanical Engineer | 2027-08-30 | 2027-09-17
29 | Mechanical design v3 / lessons learned | Mechanical Design Engineer | 2027-09-13 | 2027-10-01
30 | Procurement cycle 2 / missing parts | Electrical Design Engineer | 2027-09-20 | 2027-10-15
31 | Axis-2 fabrication & assembly | Fabrication/Assembly Technician | 2027-10-04 | 2027-10-29
32 | Axis-2 electrical integration | Electrical Technician | 2027-10-18 | 2027-11-05
33 | Axis-2 commissioning | Servo/Drive Engineer | 2027-11-01 | 2027-11-19
34 | 2-axis homing sequence | Motion Control Engineer | 2027-11-15 | 2027-12-03
35 | 2-axis firmware architecture | Firmware Engineer | 2027-11-08 | 2027-12-03
36 | Forward kinematics | Robotics Software Engineer | 2027-11-22 | 2027-12-17
37 | Inverse kinematics | Robotics Software Engineer | 2027-11-29 | 2027-12-24
38 | Trajectory generation | Motion Control Engineer | 2027-12-06 | 2027-12-31
39 | 2-axis coordinated motion | Motion Control Engineer | 2027-12-13 | 2027-12-31
40 | Jog/manual/auto modes | PLC Engineer | 2027-12-13 | 2027-12-31
41 | HMI/operator interface | PLC Engineer | 2027-12-13 | 2027-12-31
42 | Safety validation | Electrical Design Engineer | 2027-12-20 | 2027-12-31
43 | Calibration & zeroing | Motion Control Engineer | 2027-12-20 | 2027-12-31
44 | Accuracy/repeatability testing | Mechanical Engineer | 2027-12-20 | 2027-12-31
45 | Payload testing – low load | Mechanical Engineer | 2027-12-27 | 2027-12-31
46 | Payload testing – target load | Mechanical Engineer | 2027-12-27 | 2027-12-31
47 | Endurance/cycle testing | Firmware Engineer | 2027-12-27 | 2027-12-31
48 | Fault injection testing | Firmware Engineer | 2027-12-27 | 2027-12-31
49 | Design improvements / final iteration | Mechanical Design Engineer | 2027-12-27 | 2027-12-31
50 | Final integrated testing | Motion Control Engineer | 2027-12-27 | 2027-12-31
51 | Documentation & BOM freeze | All | 2027-12-27 | 2027-12-31
52 | Final demo & project review | All | 2027-12-27 | 2027-12-31
Legend | Planned Work

## Dashboard
2-Axis Robot Prototype – Management Dashboard
Planned Start | 2027-01-04
Planned Finish | 2027-12-31
Calendar Span | 12 months
Working-Day Effort | ~52 weeks / 260 working days
Number of Tasks | 52
Current Hardware | Workbench + 1 AC servo + 1 servo drive
Target | 2-axis functional prototype
Recommended execution strategy
1. Start immediately with the existing servo + drive as Axis-1 bench commissioning.
2. Do mechanical design and servo sizing in parallel with Axis-1 testing.
3. Order Axis-2 servo/drive early so procurement does not become the critical path.
4. Finish electrical/safety architecture before full mechanical integration.
5. Implement homing, limits, alarms and safe-stop before high-speed motion.
6. Validate kinematics and coordinated motion only after both axes are stable.
7. Reserve the final 1–2 weeks for tuning, load testing, fault testing and documentation.

## Manpower & Responsibilities
Department | Manpower Role | Core Responsibilities | Beginner Learning Focus
Mechanical | Mechanical Design Engineer | CAD, robot architecture, dimensions, drawings, tolerances and design revisions. | CAD, GD&T basics, robot joints, load paths, tolerances, drawing release.
Mechanical | Mechanical Engineer | Load calculations, gearbox/bearing/shaft/coupling selection, alignment, testing and mechanical validation. | Torque/inertia, gearbox, bearings, shafts, coupling, alignment and backlash.
Mechanical | Fabrication/Assembly Technician | Fabrication, machining coordination, assembly, fastening and inspection. | Machining/fabrication basics, assembly sequence, torqueing and inspection.
Electrical | Electrical Design Engineer | Power/control architecture, schematic, protection, grounding, safety and panel design. | 24V/AC power, protection, grounding, safety circuits, schematics and panel design.
Electrical | Servo/Drive Engineer | Servo/drive selection, parameters, wiring, commissioning, tuning and fault diagnosis. | Servo basics, encoder, drive parameters, tuning, alarms and commissioning.
Electrical | Electrical Technician | Panel assembly, power/control wiring, terminals, connectors and electrical testing. | Wiring practice, terminals, ferrules, shielding, grounding and testing.
Firmware | Firmware Engineer | Controller firmware, I/O, communication, diagnostics, state machine and fault handling. | C/embedded basics, I/O, communication, state machines, diagnostics and debugging.
Firmware/Controls | Motion Control Engineer | Position/speed control, homing, limits, trajectory, synchronization, calibration and tuning. | Feedback control, homing, limits, trajectory, tuning and repeatability.
Controls | PLC Engineer | PLC logic, I/O mapping, HMI, sequences, drive communication and interlocks. | PLC programming, I/O, HMI, sequences, interlocks and drive communication.
Firmware/Robotics | Robotics Software Engineer | Kinematics, trajectory/application software and robot command handling. | Coordinate systems, forward/inverse kinematics and trajectory programming.
All | All | Cross-functional review, integration, documentation and project acceptance. | Cross-functional learning and integration.