## Sheet1
S.no | Task description | Duration | Planned |  | Actual |  | Status
|  |  | Start date | Stop date | Start date | Stop date
1 | Firmware
1.1 | Understanding project requirements |  | 25.07.26 | 01.08.26 | 25.07.26 | 01.08.26 | Completed
1.2 | GPIO initialization |  | 01.08.26 | 05.08.26 | 01.08.26 | 05.08.26 | Completed
1.3 | Ethernet init and working |  | 06.08.26 | 07.08.26 | 06.08.26 | 07.08.26 | Completed
1.4 | MQTT firmware development and connect |  | 06.08.26 | 08.08.26 | 06.08.26 | 08.08.26 | Completed
1.5 | RS485 modbus communication |  | 10.08.26 | 12.08.26 | 10.08.26 | 12.08.26 | Completed
1.6 | Modbus TCP communication |  | 12.08.26 | 13.08.26 | 12.08.26 | 13.08.26 | Completed
1.7 | PWM and counter for testing |  | 14.08.26 | 14.08.26 | 14.08.26 | 14.08.26 | Completed
1.8 | FREERTOS implementation |  | 14.08.26 | 20.08.26 | 14.08.26 | 20.08.26 | Completed
1.9 | Cycletime calc and publishing |  | 20.08.26 | 25.08.26 | 20.08.26 | 25.08.26 | Completed
1.1 | Flash storage and configurable variable |  | 26.08.26 | 01.09.26 | 26.08.26 | 01.09.26 | Completed
1.11 | Web page configuration |  | 02.09.26 | 09.09.26 | 02.09.26 | 09.09.26 | Completed
1.12 | Brownout reset, watch dog |  | 09.09.26 | 16.09.26 | 09.09.26 | 19.09.26 | Completed
1.13 | Raw partition development for flash storage |  | 16.09.26 | 18.09.26 | 16.09.26 | 18.09.26 | Completed
1.14 | Mechanism to recover part count after power off and on |  | 21.09.26 | 23.09.26 | 21.09.26 |  | In Progress
1.15 | Continous testing after every step |  | 25.07.26 | 30.09.26 | 25.07.26 |  | In Progress
1.16 | SNTP time sync |  | 01.10.26 | 03.10.26 | 01.10.26 |  | Yet to start
1.17 | Documentation |  | 05.10.26 | 10.10.26 | 05.10.26 |  | Yet to start
1.19 | OTA rollback development |  | 12.10.26 | 24.10.26 | 12.10.26 |  | Yet to start
1.2 | Anamoly handling during bench test |  | 25.10.26 | 30.10.26 | 25.10.26 |  | Yet to start
2 | Hardware
2.1 | Understanding Project Requirements |  | 2026-07-28 | 2026-07-30 | 2026-07-28 | 2026-07-30 | Completed
2.2 | Requirement Finalization |  | 2026-07-31 | 2026-08-03 | 2026-07-31 | 2026-08-03 | Completed
2.3 | Interface Identification |  | 2026-08-03 | 2026-08-04 | 2026-08-03 | 2026-08-04 | Completed
2.4 | PCB Flowchart |  | 2026-08-04 | 2026-08-06 | 2026-08-04 | 2026-08-06 | Completed
2.5 | Component Selection |  | 2026-08-06 | 2026-08-12 | 2026-08-06 | 2026-08-12 | Completed
2.6 | Schematic Design |  | 2026-08-13 | 2026-08-22 | 2026-08-13 | 2026-08-22 | Completed
2.7 | Schematic Review |  | 2026-08-23 | 2026-08-24 | 2026-08-23 | 2026-08-24 | Completed
2.8 | BOM Preparartion |  | 2026-08-25 | 2026-08-31 | 2026-08-25 | 2026-08-31 | Completed
2.9 | Footprint Assigning |  | 2026-08-31 | 2026-09-02 | 2026-08-31 | 2026-09-02 | Completed
2.1 | PCB Layout Designing |  | 2026-09-02 | 2026-09-03 | 2026-09-02 | 2026-09-03 | Completed
2.11 | PCB Placement |  | 2026-09-04 | 2026-09-07 | 2026-09-04 | 2026-09-07 | Completed
2.12 | Component Procurement Quotation |  | 2026-09-08 | 2026-09-15 | 2026-08-28 | 2026-09-15 | Completed
2.13 | PCB Routing |  | 2026-09-08 | 2026-09-26 | 2026-09-08 |  | In Progress
2.14 | DRC Check |  | 2026-09-26 | 2026-09-28 |  |  | Yet to start
2.15 | PCB Review |  | 2026-09-28 | 2026-09-29 |  |  | Yet to start
2.16 | Gerber Generation |  | 2026-09-29 | 2026-09-30 |  |  | Yet to start
2.17 | Enclosure Quotation |  | 2026-09-29 | 2026-09-30 | 2026-09-21 |  | In Progress
2.18 | Component Procurement |  | 2026-09-30 | 2026-10-29 |  |  | Yet to start
2.19 | PCB Fabrication Quotation |  | 2026-10-01 | 2026-10-05 |  |  | Yet to start
2.2 | Enclosure Design |  | 2026-10-05 | 2026-10-26 |  |  | Yet to start
2.21 | Enclosure Verification |  | 2026-10-27 | 2026-10-31 |  |  | Yet to start
2.22 | PCB Assembly |  | 2026-11-02 | 2026-11-20 |  |  | Yet to start
2.23 | Assembly Inspection |  | 2026-11-20 | 2026-11-21 |  |  | Yet to start
2.24 | Hardware Testing |  | 2026-11-21 | 2026-11-27 |  |  | Yet to start
2.25 | Final BOM and Manufacturing Documents |  | 2026-11-27 | 2026-12-14 |  |  | Yet to start
2.26 | Complete IoT Device Assembly |  | 2026-12-14 | 2026-12-21 |  |  | Yet to start
2.27 | IoT Device Field Installation |  | 2026-12-21 | 2026-12-31 |  |  | Yet to start
2.28 | Hardware Design Documentation |  | 2026-12-31 | 2027-01-13 |  |  | Yet to start
2.29 | Test Result Documentation |  | 2027-01-13 | 2027-01-21 |  |  | Yet to start
2.3 | Feedback and Phase 2 Updation |  | 2027-01-21 | 2027-01-28 |  |  | Yet to start