## Slide 1
LGB
OPERATIONS TECHNOLOGY
October 2026
Weekly Project Progress
Robotic Automation Projects
Stellantis • Daimler • Helical • Ather • BMW RAD
LGB | Operations Technology
LGB
OPERATIONS TECHNOLOGY
October 2026
Weekly Project Progress
Robotic Automation Projects
LGB | Operations Technology
Stellantis • Daimler • Helical • Ather • BMW RAD

## Slide 2
PROJECT OVERVIEW
S.No | Project | Process Scope | Robots / Cobots | Start Date | End Date | Current Status
1 | Stellantis line 1-Phase | OP10 , Ultrasonic washing , Vision , OilWashing | 2 × UR12e Cobots | 07-07-2025 | 20-07-2026 | Installation & inprogress
2 | Helical Line | OP10 → OP20 | 2 UR12e Cobot + 1 yaskawa 20kg robot | 31-03-2026 | 20-10-2026 | 2 Cobot cell installation & commissioning inprogress
3 | Daimler Line | OP10 → OP20 | 4 × UR12e Cobots | 24-04-2026 | 15-10-2026 | One cell production trail done, To start program for next cell
4 | Ather Line | OP10 → OP20 | 5 × ABB 12kg Cobots | 15-02-2026 | 24-10-2026 | Waiting for FAT
5 | BMW RAD Line | OP10 → OP20→OP30→OP40 | 4 Cobots + 1 AMR | 02-02-2026 | 28-10-2026 | DAP Review Completed, 24.10.2026 Materail Inward
WEEKLY REPORT
LGB | Operations Technology

## Slide 3
STELLANTIS LINE - PHASE 1
WEEK 02 (PLAN vs ACTUAL)
WEEK 03 (PLANNED ACTIVITY)
S.No | Task | Responsibility | Planned |  | Actual |  | Status | Remarks
 |  |  | Start | End | Start | End |  | 
1 | OP10 Plunger mechanism Implementation | Robonetics | 01.10.2026 | 03.10.2026 | 01.10.2026 |  | OPEN | Robonetics working on Plunger
2 | UW - Complete Cobot Programming | Robonetics | 05.10.2026 | 08.10.2026 | 08.10.2026 | 15.10.2026 | CLOSE | Complete program completed
3 | UW - Oil dipping station grouting | LGB/Robenetics | 07.10.2026 | 07.10.2026 | 14.10.2026 |  | OPEN | Station position done and grouting pending for robonetics team input
4 | UW - Metal bin modification for programming | LGB | 07.10.2026 | 07.10.2026 | 13.10.2026 | 13.10.2026 | CLOSE | Completed
5 | UW - Complete Trail without pusher setup | Robonetics | 13.10.2026 | 16.10.2026 | 15.10.2026 |  | OPEN | Bin in lifter not aligned in same position on continous process
S.No | Task | Responsibility | Planned |  | Actual |  | Status | Remarks
 |  |  | Start | End | Start | End |  | 
1 | Alignment correction for bin in lifter | Robonetics | 20.10.2026 | 22.10.2026 |  |  |  | Design Team work
2 | Continous running of UW station | Robonetics | 22.10.2026 | 24.10.2026 |  |  |  | 
WEEKLY REPORT
LGB | Operations Technology

## Slide 4
STELLANTIS LINE - PHASE 1
Stellantis line UW cobot program completion
WEEKLY REPORT
LGB | Operations Technology

## Slide 5
LGB l Operations Technology
HELICAL LINE
WEEK 02 (PLAN vs ACTUAL)
WEEK 03 (PLANNED ACTIVITY)
S.No | Task | Responsibility | Planned |  | Actual |  | Status | Remarks
 |  |  | Start | End | Start | End |  | 
1 | Cobot cells Mechanical setup assembly and grouting | Robonetics | 07.10.2026 | 08.10.2026 | 09.10.2026 |  | OPEN | Waiting for part confirmation and trail taken for 1790 OP10 machined part with exixting setup and shared for quality check. Confirmed line operator for scratch issue and observed parallelism around 100-200 micron
2 | Cobot programming for 1 cell | Robonetics | 08.10.2026 | 10.10.2026 | 15.10.2026 |  | OPEN | 
3 | Completion of PLC logic for 1 cell | Robonetics | 12.10.2026 | 13.10.2026 | 15.10.2026 |  | OPEN | 
4 | Complete trail in 1 cell | Robonetics | 12.10.2026 | 14.10.2026 |  |  | OPEN | 
5 | Machine Movement for robot cells | LGB | 08.10.2026 | 08.10.2026 |  |  | OPEN | Pending with plant team
6 | Robot reach check confirmation | LGB | 16.10.2026 | 17.10.2026 |  |  | OPEN | 
S.No | Task | Responsibility | Planned |  | Actual |  | Status | Remarks
 |  |  | Start | End | Start | End |  | 
1 | Confirmation on 1790 part to proceed | LGB | 17.10.2026 | 17.10.2026 |  |  |  | 
2 | Cobot programming for 1 cell | Robonetics | 20.10.2026 | 21.10.2026 |  |  |  | 
3 | Complete trail in 1 cell for 1790 | Robonetics | 22.10.2026 | 23.10.2026 |  |  |  | Flipping station pending
4 | Confirmation on parts for commissioning | LGB | 20.10.2026 | 20.10.2026 |  |  |  | 
WEEKLY REPORT
LGB | Operations Technology

## Slide 6
LGB l Operations Technology
HELICAL LINE
HELICAL LINE 1790 CELL TRAIL ON SCRATCH WITH OP10 MACHINED PARTS
WEEKLY REPORT
LGB | Operations Technology

## Slide 7
LGB l Operations Technology
DAIMLER LINE
WEEK 02 (PLAN vs ACTUAL)
WEEK 03 (PLANNED ACTIVITY)
WEEKLY REPORT
LGB | Operations Technology
S.No | Task | Responsibility | Planned |  | Actual |  | Status | Remarks
 |  |  | Start | End | Start | End |  | 
1 | 1361 - Production trail | Multivista | 05.10.2026 | 09.10.2026 | 05.10.2026 | 10.10.2026 | CLOSE | 
2 | 1361 - HMI stand mounting | Multivista | 09.10.2026 | 09.10.2026 | 09.10.2026 | 09.10.2026 | CLOSE | 
3 | LMW team support I/O configuration | Multivista | 09.10.2026 | 13.10.2026 | 09.10.2026 |  | OPEN | 2 machines completed, 2 machines planned on 17.10.2026
4 | Remaining cell cobot installation | Multivista | 12.10.2026 | 13.10.2026 | 14.10.2026 | 14.10.2026 | CLOSE | 
5 | Remaining cell mechanical assembly | Multivista | 12.10.2026 | 14.10.2026 | 16.10.2026 |  | OPEN | Delayed in confirmation of part and machine handover from plant team
6 | Cobot programming for 1 cell - 1217 | Multivista | 14.10.2026 | 15.10.2026 |  |  | OPEN | 
7 | Completion of PLC logic for 1 cell - 1217 | Multivista | 14.10.2026 | 16.10.2026 |  |  | OPEN | 
8 | Complete trail in 1 cell - 1217 | Multivista | 16.10.2026 | 17.10.2026 |  |  | OPEN | 
S.No | Task | Responsibility | Planned |  | Actual |  | Status | Remarks
 |  |  | Start | End | Start | End |  | 
1 | 1361 - Handover to production | Multivista/LGB | 22.10.2026 | 22.10.2026 |  |  |  | 
2 | Dry run and Cycle time optimization - 1217 | Multivista | 23.10.2026 | 23.10.2026 |  |  |  | 
3 | Electrical wiring and cable connections for all cells | Multivista | 16.10.2026 | 19.10.1026 |  |  |  | 

## Slide 8
DAIMLER LINE
DAIMLER LINE 1217 PART INPUT TABLE & OUTPUT TABLE IS GROUTED
DAIMLER LINE 4 CELL COBOT GROUTING
WEEKLY REPORT
LGB | Operations Technology

## Slide 9
LGB l Operations Technology
BMW - RAD LINE
WEEK 03 (PLANNED ACTIVITY)
WEEKLY REPORT
LGB | Operations Technology
S.No | Task | Responsibility | Planned |  | Actual |  | Status | Remarks
 |  |  | Start | End | Start | End |  | 
1 | OP40 Three cell layout redesign in DAP | Robonetics | 15.10.2026 | 21.10.2026 |  |  |  | 
2 | Inward of materails commited | Robonetics | 15.10.2026 | 24.10.2026 |  |  |  | 
DAP Discussion MOM Points

## Slide 10
OTHER PROJECT DETAILS
WEEKLY REPORT
LGB | Operations Technology
S.No | Task | Responsibility | Planned | Status | Remarks
1 | Ather Material Readiness | Melss | 21.10.2026 | In-Progress | FAT planned on 26.10.2026 - Commited by Melss
2 | Camera Installation in Diamler line | OT Team | 17.10.2026 | In-Progress | Temporary camera view changed with existing, New camera in Capex budget
3 | Texsonics robot trail | OT Team/Texsonics | 28.10.2026 | In-Progress | Tenative on trail date. Quotation to be shared on 22.10.2026

## Slide 11
Thank You
October 2026
Weekly Project progress review
LGB | Operations Technology